## Sheet1
Task | Start Date | End Date | Status
Requirement Gathering | 2025-07-10 | 2025-07-14 | Completed
Design Architecture | 2025-07-15 | 2025-07-19 | Ongoing
Development | 2025-07-20 | 2025-07-31 | Pending
Testing | 2025-08-01 | 2025-08-09 | Pending
Deployment | 2025-08-10 | 2025-08-15 | Pending